## Sheet1
WBS | Task Name | Duration(Days) | Start | Finish | W1(02/02) | W2(09/02) | W3(16/02) | W4(23/02) | W5(02/03) | W6(09/03) | W7(16/03) | W8(23/03) | W9(30/03) | W10(06/04) | W11(13/04) | W12(20/04)
1.0 | Project Planning | 49 days | 2026-02-02 | 30/3/2026
1.1 | Preliminary Planning | 7 days | 2026-02-02 | 2026-08-02
1.1.1 | Study background of the project problem | 1 days | 2026-08-02 | 2026-08-02
1.1.1.1 | Define problem statements | 1 days | 2026-09-02 | 2026-09-02
1.1.1.2 | Define project objectives | 1 days | 2026-10-02 | 2026-10-02
1.1.2 | Define project scope | 1 days | 2026-11-02 | 2026-11-02
1.1.3 | Define project proposed solution | 1 days | 2026-12-02 | 2026-12-02
1.1.4 | Define project proposed approach | 1 days | 13/2/2026 | 13/2/2026
1.1.5 | Define project out-of-scope | 1 days | 14/2/2026 | 14/2/2026
1.2 | Literature Review | 14 days | 15/2/2026 | 2026-09-03
1.2.1 | Review on Development Methodology | 7 days | 15/2/2026 | 22/2/2026
1.2.1.1 | Review on Waterfall Development Methodology | 1 days | 16/2/2026 | 16/2/2026
1.2.1.2 | Review on Agile Methodology | 1 days | 17/2/2026 | 17/2/2026
1.2.1.3 | Review on Prototyping Model | 1 days | 18/2/2026 | 18/2/2026
1.2.1.4 | Review on Rapid Application Development (RAD) | 1 days | 19/2/2026 | 19/2/2026
1.2.1.5 | Comparison of Development Methodologies | 3 days | 20/2/2026 | 22/2/2026
1.2.2 | Review on Mobile Application Framework | 3 days | 23/2/2026 | 25/2/2026
1.2.2.1 | Review on React Native | 1 days | 26/2/2026 | 26/2/2026
1.2.2.2 | Review on Flutter | 1 days | 27/2/2026 | 27/2/2026
1.2.2.3 | Comparison of Mobile Application Frameworks | 1 days | 28/2/2026 | 2026-01-03
1.2.3 | Review on Existing Applications | 4 days | 2026-02-03 | 2026-05-03
1.2.3.1 | Review on Ellicares | 2 days | 2026-06-03 | 2026-07-03
1.2.3.2 | Review on XDementia | 2 days | 2026-08-03 | 2026-09-03
1.3 | Methodology and Work Plan | 7 days | 2026-10-03 | 16/3/2026
1.3.1 | Choose Methodology | 2 days | 2026-10-03 | 2026-11-03
1.3.2 | Project Scheduling | 2 days | 2026-12-03 | 13/3/2026
1.3.2.1 | Work Breakdown Structure | 2 days | 14/3/2026 | 15/3/2026
1.3.2.2 | Gantt Chart | 1 days | 16/3/2026 | 16/3/2026
1.4 | Project and Design Specification | 21 days | 17/3/2026 | 30/3/2026
1.4.1 | Requirement Specification | 2 days | 17/3/2026 | 18/3/2026
1.4.1.1 | Identify Functional Requirement | 1 days | 19/3/2026 | 19/3/2026
1.4.1.2 | Identify Non-Functional Requirement | 1 days | 20/3/2026 | 20/3/2026
1.4.2 | Create UML Diagram | 5 days | 21/3/2026 | 25/3/2026
1.4.2.1 | Develop Use Case Diagram | 2 days | 26/3/2026 | 27/3/2026
1.4.2.2 | Define Use Case Descriptions | 3 days | 28/3/2026 | 30/3/2026
2.0 | Design and Prototyping | 28 days | 31/3/2026 | 21/4/2026
2.1 | First Iteration | 7 days | 31/3/2026 | 2026-07-04
2.1.1 | Design User Interface | 2 days | 2026-01-04 | 2026-02-04
2.1.2 | Build Low-Fidelity Prototype | 2 days | 2026-03-04 | 2026-04-04
2.1.3 | Evaluation and Gathering Feedback | 2 days | 2026-05-04 | 2026-06-04
2.1.4 | Review Prototype | 1 days | 2026-07-04 | 2026-07-04
2.2 | Second Iteration | 14 days | 2026-08-04 | 21/4/2026
2.2.1 | Develop Essential Features | 7 days | 2026-08-04 | 14/4/2026
2.2.1.1 | User Authentication | 1 days | 2026-08-04 | 2026-08-04
2.2.1.2 | Task and Medication Reminder Module | 1 days | 2026-09-04 | 2026-09-04
2.2.1.3 | Notification System | 1 days | 2026-10-04 | 2026-10-04
2.2.1.4 | Cognitive Exercises Module | 1 days | 2026-11-04 | 2026-11-04
2.2.1.5 | Gamification Module | 1 days | 2026-12-04 | 2026-12-04
2.2.1.6 | Caregiver Dashboard | 2 days | 13/4/2026 | 14/4/2026
2.2.2 | Database Design | 3 days | 15/4/2026 | 17/4/2026
2.2.3 | Evaluation and Gathering Feedback | 2 days | 18/4/2026 | 19/4/2026
2.2.4 | Review Prototype | 2 days | 20/4/2026 | 21/4/2026
|  |  | Start date | End date | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14
3.0 | Development phase | 56 days | 2026-06-15 | 2026-08-09
3.1 | Develop Prototype into Final Product | 56 days | 2026-06-15 | 2026-08-09
3.1.1 | Configure Development Environment | 3 days | 2026-06-15 | 2026-06-17
3.1.1.1 | User Authentication | 1 day | 2026-06-15 | 2026-06-15
3.1.1.2 | Connect the application to Firebase | 1 day | 2026-06-15 | 2026-06-15
3.1.1.3 | Configure Firebase Authentication | 1 day | 2026-06-16 | 2026-06-16
3.1.1.4 | Configure Cloud Firestore database | 1 day | 2026-06-17 | 2026-06-17
3.1.2 | Develop Authentication, Access and Settings | 7 days | 2026-06-15 | 2026-06-21
3.1.2.1 | Develop caregiver registration | 1 day | 2026-06-15 | 2026-06-15
3.1.2.2 | Develop caregiver and patient login | 1 day | 2026-06-16 | 2026-06-16
3.1.2.3 | Implement role-based dashboard navigation | 1 day | 2026-06-17 | 2026-06-17
3.1.2.4 | Implement role-based side drawer | 1 day | 2026-06-18 | 2026-06-18
3.1.2.5 | Develop font-size settings | 1 day | 2026-06-19 | 2026-06-19
3.1.2.6 | Implement secure logout | 2 days | 2026-06-20 | 2026-06-21
3.1.3 | Develop Patient Management Module | 9 days | 2026-06-18 | 2026-06-26
3.1.3.1 | Develop patient account creation | 1 day | 2026-06-18 | 2026-06-18
3.1.3.2 | Implement caregiver-patient account linking | 1 day | 2026-06-19 | 2026-06-19
3.1.3.3 | Record dementia stage and type | 1 day | 2026-06-20 | 2026-06-20
3.1.3.4 | Develop patient information updating | 2 days | 2026-06-21 | 2026-06-22
3.1.3.5 | Develop patient account unlinking | 1 day | 2026-06-23 | 2026-06-23
3.1.3.6 | Implement patient password reset | 1 day | 2026-06-24 | 2026-06-24
3.1.3.7 | Develop patient list interface | 2 days | 2026-06-25 | 2026-06-26
3.1.4 | Develop Task and Medication Module | 19 days | 2026-06-22 | 2026-07-10
3.1.4.1 | Develop task and medication creation | 1 day | 2026-06-22 | 2026-06-22
3.1.4.2 | Implement patient task assignment | 2 days | 2026-06-23 | 2026-06-24
3.1.4.3 | Implement medication dosage recording | 2 days | 2026-06-25 | 2026-06-26
3.1.4.4 | Develop task and medication updating | 1 day | 2026-06-27 | 2026-06-27
3.1.4.5 | Develop task and medication deletion | 2 days | 2026-06-28 | 2026-06-29
3.1.4.6 | Implement daily task timeline | 2 days | 2026-06-30 | 2026-07-01
3.1.4.7 | Implement task status management | 2 days | 2026-07-02 | 2026-07-03
3.1.4.8 | Implement occurrence-specific task statuses | 1 day | 2026-07-04 | 2026-07-04
3.1.4.9 | Develop task history and status filtering | 2 days | 2026-07-05 | 2026-07-06
3.1.4.10 | Develop patient task calendar | 2 days | 2026-07-07 | 2026-07-08
3.1.4.11 | Implement dashboard progress calculation | 2 days | 2026-07-09 | 2026-07-10
3.1.5 | Develop Recurrence and Notification Module | 19 days | 2026-06-29 | 2026-07-17
3.1.5.1 | Implement daily/weekly/monthly/yearly/custom recurrence | 2 days | 2026-06-29 | 2026-06-30
3.1.5.2 | Implement optional recurrence end dates | 2 days | 2026-07-01 | 2026-07-02
3.1.5.3 | Develop local notification scheduling | 3 days | 2026-07-03 | 2026-07-05
3.1.5.4 | Implement configurable reminder intervals | 2 days | 2026-07-06 | 2026-07-07
3.1.5.5 | Implement repeated reminder notifications | 2 days | 2026-07-08 | 2026-07-09
3.1.5.6 | Develop Complete and Missed notification actions | 3 days | 2026-07-10 | 2026-07-12
3.1.5.7 | Implement automatic missed-task processing | 2 days | 2026-07-13 | 2026-07-14
3.1.5.8 | Implement notification rescheduling and cancellation | 3 days | 2026-07-15 | 2026-07-17
3.1.6 | Develop Cognitive Games Module | 19 days | 2026-07-06 | 2026-07-24
3.1.6.1 | Develop Alzheimer’s early and middle stage game set | 3 days | 2026-07-06 | 2026-07-08
3.1.6.2 | Develop vascular dementia early and middle stage game set | 3 days | 2026-07-09 | 2026-07-11
3.1.6.3 | Implement dementia profile-based game selection | 3 days | 2026-07-12 | 2026-07-14
3.1.6.4 | Implement errorless guidance and hints | 3 days | 2026-07-15 | 2026-07-17
3.1.6.5 | Record cognitive-game session results | 3 days | 2026-07-18 | 2026-07-20
3.1.6.6 | Calculate game accuracy and performance | 4 days | 2026-07-21 | 2026-07-24
3.1.7 | Develop Adaptive Difficulty Module | 19 days | 2026-07-13 | 2026-07-31
3.1.7.1 | Implement per-game difficulty levels | 2 days | 2026-07-13 | 2026-07-14
3.1.7.2 | Implement automatic difficulty promotion/demotion | 3 days | 2026-07-15 | 2026-07-17
3.1.7.3 | Develop caregiver difficulty override | 3 days | 2026-07-18 | 2026-07-20
3.1.7.4 | Implement automatic adjustment freezing | 2 days | 2026-07-21 | 2026-07-22
3.1.7.5 | Record difficulty change history | 3 days | 2026-07-23 | 2026-07-25
3.1.7.6 | Develop Game Statistics interface | 3 days | 2026-07-26 | 2026-07-28
3.1.7.7 | Develop game accuracy trend chart | 3 days | 2026-07-29 | 2026-07-31
3.1.8 | Develop Gamification and Rewards Module | 19 days | 2026-07-06 | 2026-07-24
3.1.8.1 | Implement daily login streak | 2 days | 2026-07-06 | 2026-07-07
3.1.8.2 | Implement seven-day reward cycle | 2 days | 2026-07-08 | 2026-07-09
3.1.8.3 | Implement missed-day streak reset | 2 days | 2026-07-10 | 2026-07-11
3.1.8.4 | Award task and medication completion points | 2 days | 2026-07-12 | 2026-07-13
3.1.8.5 | Award cognitive-game completion points | 2 days | 2026-07-14 | 2026-07-15
3.1.8.6 | Calculate patient level and progress | 2 days | 2026-07-16 | 2026-07-17
3.1.8.7 | Develop streak and points interface | 2 days | 2026-07-18 | 2026-07-19
3.1.8.8 | Implement points based reward game unlocking | 2 days | 2026-07-20 | 2026-07-21
3.1.8.9 | Integrate external reward games | 3 days | 2026-07-22 | 2026-07-24
3.1.9 | Develop Monitoring and Analytics Module | 19 days | 2026-07-20 | 2026-08-07
3.1.9.1 | Calculate task completion rate | 2 days | 2026-07-20 | 2026-07-21
3.1.9.2 | Calculate cognitive-game performance | 2 days | 2026-07-22 | 2026-07-23
3.1.9.3 | Calculate average hint usage | 3 days | 2026-07-24 | 2026-07-26
3.1.9.4 | Develop performance trend charts | 2 days | 2026-07-27 | 2026-07-28
3.1.9.5 | Develop cognitive-game rankings | 2 days | 2026-07-29 | 2026-07-30
3.1.9.6 | Develop completed-task category analysis | 3 days | 2026-07-31 | 2026-08-02
3.1.9.7 | Implement risk indicator | 2 days | 2026-08-03 | 2026-08-04
3.1.9.8 | Implement cognitive-decline risk signal | 3 days | 2026-08-05 | 2026-08-07
3.1.10 | Integrate and Refine Final Product | 7 days | 2026-08-03 | 2026-08-09
4.0 | Testing phase | 57 days | 2026-07-13 | 2026-09-07
4.1 | Prepare Testing Documentation | 5 days | 2026-07-13 | 2026-07-17
4.1.1 | Identify test objectives | 1 day | 2026-07-13 | 2026-07-13
4.1.2 | Prepare test environment | 1 day | 2026-07-14 | 2026-07-14
4.1.3 | Prepare test accounts and data | 1 day | 2026-07-15 | 2026-07-15
4.1.4 | Map test cases to functional requirements | 1 day | 2026-07-16 | 2026-07-16
4.1.5 | Define expected test results | 1 day | 2026-07-17 | 2026-07-17
4.2 | Unit testing | 12 days | 2026-07-20 | 2026-07-31
4.2.1 | authentication and role access | 1 day | 2026-07-20 | 2026-07-20
4.2.2 | patient management functions | 1 day | 2026-07-21 | 2026-07-21
4.2.3 | task and medication functions | 2 days | 2026-07-22 | 2026-07-23
4.2.4 | recurrence calculations | 1 day | 2026-07-24 | 2026-07-24
4.2.5 | cognitive game calculations | 1 day | 2026-07-25 | 2026-07-25
4.2.6 | adaptive difficulty rules | 2 days | 2026-07-26 | 2026-07-27
4.2.7 | gamification calculations | 1 day | 2026-07-28 | 2026-07-28
4.2.8 | risk evaluation logic | 1 day | 2026-07-29 | 2026-07-29
4.2.9 | unit testing results | 2 days | 2026-07-30 | 2026-07-31
4.3 | Integration Testing | 12 days | 2026-08-03 | 2026-08-14
4.3.1 | authentication and role navigation integration | 1 day | 2026-08-03 | 2026-08-03
4.3.2 | caregiver and patient account integration | 1 day | 2026-08-04 | 2026-08-04
4.3.3 | task assignment and dashboard integration | 2 days | 2026-08-05 | 2026-08-06
4.3.4 | recurring tasks and notification integration | 1 day | 2026-08-07 | 2026-08-07
4.3.5 | task responses and progress updates | 1 day | 2026-08-08 | 2026-08-08
4.3.6 | game sessions and adaptive difficulty integration | 2 days | 2026-08-09 | 2026-08-10
4.3.7 | points and reward game integration | 1 day | 2026-08-11 | 2026-08-11
4.3.8 | risk indicator integration | 1 day | 2026-08-12 | 2026-08-12
4.3.9 | Record integration testing results | 2 days | 2026-08-13 | 2026-08-14
4.4 | System testing | 12 days | 2026-08-10 | 2026-08-21
4.4.1 | complete caregiver workflow | 1 day | 2026-08-10 | 2026-08-10
4.4.2 | complete patient workflow | 2 days | 2026-08-11 | 2026-08-12
4.4.3 | task and medication lifecycle | 2 days | 2026-08-13 | 2026-08-14
4.4.4 | recurring reminder behaviour | 1 day | 2026-08-15 | 2026-08-15
4.4.5 | cognitive-game workflow | 2 days | 2026-08-16 | 2026-08-17
4.4.6 | activity monitoring and analytics | 2 days | 2026-08-18 | 2026-08-19
4.4.7 | Record system testing results | 2 days | 2026-08-20 | 2026-08-21
4.5 | Usability testing | 9 days | 2026-08-17 | 2026-08-25
4.5.1 | Prepare usability testing questionnaire | 1 day | 2026-08-17 | 2026-08-17
4.5.2 | Select usability testing participants | 1 day | 2026-08-18 | 2026-08-18
4.5.3 | Conduct usability testing | 1 day | 2026-08-19 | 2026-08-19
4.5.4 | Collect System Usability Scale responses | 2 days | 2026-08-20 | 2026-08-21
4.5.5 | Calculate the average SUS score | 1 day | 2026-08-22 | 2026-08-22
4.5.6 | Analyse participant feedback | 1 day | 2026-08-23 | 2026-08-23
4.5.7 | Record usability testing results | 2 days | 2026-08-24 | 2026-08-25
4.6 | User-Acceptance testing | 12 days | 2026-08-24 | 2026-09-04
4.6.1 | Prepare user acceptance test cases | 2 days | 2026-08-24 | 2026-08-25
4.6.2 | Conduct caregiver and patient acceptance testing | 2 days | 2026-08-26 | 2026-08-27
4.6.3 | Compare actual and expected results | 2 days | 2026-08-28 | 2026-08-29
4.6.4 | Record pass or fail status | 2 days | 2026-08-30 | 2026-08-31
4.6.5 | Confirm functional requirement acceptance | 2 days | 2026-09-01 | 2026-09-02
4.6.6 | Record user acceptance testing results | 2 days | 2026-09-03 | 2026-09-04
4.7 | Resolve Defects | 3 days | 2026-09-05 | 2026-09-07
5.0 | Project Completion | 29 days | 2026-08-17 | 2026-09-14
5.1 | Prepare FYP poster | 9 days | 2026-08-17 | 2026-08-25
5.2 | Submit FYP poster | 1 day | 2026-08-26 | 2026-08-26
5.3 | Prepare final project report | 15 days | 2026-08-27 | 2026-09-10
5.4 | Submit Final Project Report | 1 day | 2026-09-11 | 2026-09-11
5.5 | Prepare Final Presentation | 3 days | 2026-09-12 | 2026-09-14